## README
HEIRLOOM EXPERIMENT MATRIX
HEIRLOOM: Inherited Alignment Backdoors Across LLM Derivative Lineages
Scope of the current controlled study: DPO-stage compromise. Reward model and PPO are extension X2.
Synchronized with HEIRLOOM_Research_Proposal_Internal.docx (master). Refreshed 27 September 2026.
SHEETS
Experiments one row per experiment ID with goal, factors, dependencies and phase
Conditions the enumerated run list for the core experiments
Models model roles, licences and placement
Datasets source and derived datasets with roles
Metrics the single definition of every metric
AuditGroups the six model control groups for E7 and the contrasts they enable
Decisions decision identifiers and the reason for each
Timeline the 23-week schedule, the go/no-go gate and the release plan
CONVENTIONS
lambda is the weight assigned to the CLEAN merge partner. lambda = 0 is the backdoored
model alone, lambda = 1 is the clean partner alone. Survival is expected to DECREASE
as lambda increases. This convention is used in every sheet, config and plot.
Seven core experiments, E1 to E7, in two phases. Nothing is numbered E7 or higher,
so the count of core experiments and the highest core identifier always agree.
Extensions are X1 to X6 and none is required for the paper to have a result.
Poisoning rate: PRIMARY 5 percent of training rows. Sensitivity sweep at 1, 2.5, 5
and 10 percent on trigger A with two seeds, inside E1.
Provenance labels: [S] supervisor idea, [SH] supervisor hypothesis, [R] our refinement,
[L] literature, [I] our implementation decision.
NO CELL IN THIS WORKBOOK CONTAINS AN EXPERIMENTAL RESULT.
No ASR, AUROC, survival ratio, transmissibility, runtime or GPU-hour figure is recorded,
because none has been measured. Result columns are left empty on purpose.

## Experiments
Experiments and stable identifiers
Seven core experiments, E1 to E7, in two phases: E1 to E6 phase one, E7 audit phase two. Extensions X1 to X6 are not part of the professor-facing core proposal. Nothing is numbered E7 or higher.
ID | Name | Phase | Question it answers | What changes | What stays fixed | Depends on | Primary outputs
P0 | Pilot on the development model | Phase one, gate | Does the whole pipeline run end to end, and are the training settings viable? | Nothing; it is a feasibility run | All design choices as planned | Frozen data | Pilot report, settings consumed by E1
E1 | Matched DPO and SFT ancestors | Phase one, critical path | Can both stages be brought to the same starting attack strength from the same rows? | Training stage, trigger, poisoning rate | Base model, source rows, poisoned index set, target text, adapter, budget, evaluation | P0 | Matched ancestors, checkpoint selection report, ancestors.csv
E2 | Quantization | Phase one | How much survives compression for deployment? | Precision and method: INT8, NF4, GPTQ INT4 | Ancestor, calibration set, evaluation, decoding | E1 | Quantized descendants, survival per method
E3 | Continued clean SFT | Phase one | Does benign fine-tuning remove it, and how much data does that take? | Clean examples seen (four checkpoints); adapter rank secondary | Learning rate, data source, ancestor, evaluation | E1 | Decay curve against clean examples seen
E4 | Model merging | Phase one | Does merging with a clean partner dilute it, and at what clean weight? | lambda (weight on the CLEAN partner), merging method | Clean partner, base model, evaluation, toolkit version | E1 | lambda curve, recipe YAML per merged model
E5 | Distillation | Phase one | Does a student inherit it from teacher-written text alone? | Whether the trigger appears in the teacher prompt pool | Teachers, student initialisation, prompt pool, recipe | E1 | Student results in both trigger conditions
E6 | Mechanism and representation analysis | Phase one | Is persistence associated with low-rank preference structure, and is it causal? | Measurement type: rank, overlap, sign, ablation | Ancestors, paired clean runs, layer set | E1 plus full-parameter implants | Rank and overlap tables, causal ablation result
E7 | HEIRLOOM-AUDIT | Phase two | What can a descendant-only audit establish, and is it inheritance-specific? | Model group being scored | Audit procedure, benign pairs, calibration protocol | E1 to E5 plus groups G5 and G6 | Detection curves per contrast, baseline comparison
X1 | Poisoning-rate sweep | Extension | How does the stage effect vary with attack budget? | Poisoning rate, four or more values | Everything else | E1 | Dose-response curve
X2 | Reward model and PPO pipelines | Extension, highest value | Does the result extend from DPO to the alignment stage in general? | Alignment algorithm | Data, trigger, evaluation | E1 to E5 | Second alignment pipeline, required for a general claim
X4 | Trigger position and form sweep | Extension | Is the effect specific to a trigger design? | Trigger position and form | Stage, rate, evaluation | E1 | Trigger sensitivity table
X5 | Black-box audit variant | Extension | Can anything be established without weight access? | Access model | Model set, contrasts | E7 | Black-box detection curves
X6 | Defensive recipe recommendations | Extension | Which operation settings reliably sanitize? | Operation settings | Ancestors, evaluation | E2 to E5 | Recommended defensive recipes

## Conditions
Enumerated run list
One row per planned run or run family. The Result column is intentionally empty: nothing has been run.
Exp ID | Run identifier | Stage | Trigger | Rate | Seeds | Model | Note | Result (leave empty until measured)
E1 | E1_dpo_trigA_r05 | DPO | Trigger A | 5% | 0,1,2 | Qwen2.5-7B-Instruct | Poisoned ancestor, checkpoint-matched
E1 | E1_dpo_trigB_r05 | DPO | Trigger B | 5% | 0,1,2 | Qwen2.5-7B-Instruct | Poisoned ancestor, checkpoint-matched
E1 | E1_sft_trigA_r05 | SFT | Trigger A | 5% | 0,1,2 | Qwen2.5-7B-Instruct | Poisoned ancestor, checkpoint-matched
E1 | E1_sft_trigB_r05 | SFT | Trigger B | 5% | 0,1,2 | Qwen2.5-7B-Instruct | Poisoned ancestor, checkpoint-matched
E1 | E1_dpo_trigA_r1 | DPO | Trigger A | 1% | 0,1 | Qwen2.5-7B-Instruct | Rate sensitivity sweep. Primary rate is 5 percent; the sweep covers 1, 2.5, 5 and 10 percent on trigger A with two seeds.
E1 | E1_sft_trigA_r1 | SFT | Trigger A | 1% | 0,1 | Qwen2.5-7B-Instruct | Rate sensitivity sweep. Primary rate is 5 percent; the sweep covers 1, 2.5, 5 and 10 percent on trigger A with two seeds.
E1 | E1_dpo_trigA_r25 | DPO | Trigger A | 2.5% | 0,1 | Qwen2.5-7B-Instruct | Rate sensitivity sweep. Primary rate is 5 percent; the sweep covers 1, 2.5, 5 and 10 percent on trigger A with two seeds.
E1 | E1_sft_trigA_r25 | SFT | Trigger A | 2.5% | 0,1 | Qwen2.5-7B-Instruct | Rate sensitivity sweep. Primary rate is 5 percent; the sweep covers 1, 2.5, 5 and 10 percent on trigger A with two seeds.
E1 | E1_dpo_trigA_r10 | DPO | Trigger A | 10% | 0,1 | Qwen2.5-7B-Instruct | Rate sensitivity sweep. Primary rate is 5 percent; the sweep covers 1, 2.5, 5 and 10 percent on trigger A with two seeds.
E1 | E1_sft_trigA_r10 | SFT | Trigger A | 10% | 0,1 | Qwen2.5-7B-Instruct | Rate sensitivity sweep. Primary rate is 5 percent; the sweep covers 1, 2.5, 5 and 10 percent on trigger A with two seeds.
E1 | E1_dpo_clean | DPO | none | 0% | 0,1,2 | Qwen2.5-7B-Instruct | Clean control ancestor, bypasses matching
E1 | E1_sft_clean | SFT | none | 0% | 0,1,2 | Qwen2.5-7B-Instruct | Clean control ancestor, bypasses matching
E2 | E2_<ancestor>_int8 | inherit | inherit | inherit | inherit | inherit | Quantization int8, applied to every E1 ancestor including clean controls
E2 | E2_<ancestor>_nf4 | inherit | inherit | inherit | inherit | inherit | Quantization nf4, applied to every E1 ancestor including clean controls
E2 | E2_<ancestor>_gptq_int4 | inherit | inherit | inherit | inherit | inherit | Quantization gptq_int4, applied to every E1 ancestor including clean controls
E2 | E2_<ancestor>_gguf_q4_k_m | inherit | inherit | inherit | inherit | inherit | Quantization gguf_q4_k_m, applied to every E1 ancestor including clean controls
E3 | E3_<ancestor>_ck1 | inherit | inherit | inherit | inherit | inherit | Continued clean SFT, checkpoint ck1 of one epoch over 10,000 examples
E3 | E3_<ancestor>_ck2 | inherit | inherit | inherit | inherit | inherit | Continued clean SFT, checkpoint ck2 of one epoch over 10,000 examples
E3 | E3_<ancestor>_ck3 | inherit | inherit | inherit | inherit | inherit | Continued clean SFT, checkpoint ck3 of one epoch over 10,000 examples
E3 | E3_<ancestor>_ck4 | inherit | inherit | inherit | inherit | inherit | Continued clean SFT, checkpoint ck4 of one epoch over 10,000 examples
E4 | E4_<ancestor>_linear_lam0.10 | inherit | inherit | inherit | inherit | inherit | Linear merge, lambda = 0.10 on the CLEAN partner
E4 | E4_<ancestor>_linear_lam0.30 | inherit | inherit | inherit | inherit | inherit | Linear merge, lambda = 0.30 on the CLEAN partner
E4 | E4_<ancestor>_linear_lam0.50 | inherit | inherit | inherit | inherit | inherit | Linear merge, lambda = 0.50 on the CLEAN partner
E4 | E4_<ancestor>_linear_lam0.70 | inherit | inherit | inherit | inherit | inherit | Linear merge, lambda = 0.70 on the CLEAN partner
E4 | E4_<ancestor>_linear_lam0.90 | inherit | inherit | inherit | inherit | inherit | Linear merge, lambda = 0.90 on the CLEAN partner
E4 | E4_<ancestor>_ties_lam0.30 | inherit | inherit | inherit | inherit | inherit | TIES merge, lambda = 0.30 on the CLEAN partner
E4 | E4_<ancestor>_ties_lam0.50 | inherit | inherit | inherit | inherit | inherit | TIES merge, lambda = 0.50 on the CLEAN partner
E4 | E4_<ancestor>_ties_lam0.70 | inherit | inherit | inherit | inherit | inherit | TIES merge, lambda = 0.70 on the CLEAN partner
E4 | E4_<ancestor>_dare_lam0.30 | inherit | inherit | inherit | inherit | inherit | DARE merge, lambda = 0.30 on the CLEAN partner
E4 | E4_<ancestor>_dare_lam0.50 | inherit | inherit | inherit | inherit | inherit | DARE merge, lambda = 0.50 on the CLEAN partner
E4 | E4_<ancestor>_dare_lam0.70 | inherit | inherit | inherit | inherit | inherit | DARE merge, lambda = 0.70 on the CLEAN partner
E5 | E5_<teacher>_qwen1.5b_same_family_trigger_absent | inherit | inherit | inherit | inherit | qwen1.5b_same_family | Distillation. Teachers: 8 (6 poisoned = 2 stages x trigger A x 3 seeds, plus 2 clean controls). Prompt pool condition: trigger_absent. Student never sees poisoned data. The cross-family student runs on the 2 stages at seed 0 plus the 2 clean controls.
E5 | E5_<teacher>_qwen1.5b_same_family_trigger_present_small_fraction | inherit | inherit | inherit | inherit | qwen1.5b_same_family | Distillation. Teachers: 8 (6 poisoned = 2 stages x trigger A x 3 seeds, plus 2 clean controls). Prompt pool condition: trigger_present_small_fraction. Student never sees poisoned data. The cross-family student runs on the 2 stages at seed 0 plus the 2 clean controls.
E5 | E5_<teacher>_smollm2_1.7b_cross_family_trigger_absent | inherit | inherit | inherit | inherit | smollm2_1.7b_cross_family | Distillation. Teachers: 8 (6 poisoned = 2 stages x trigger A x 3 seeds, plus 2 clean controls). Prompt pool condition: trigger_absent. Student never sees poisoned data. The cross-family student runs on the 2 stages at seed 0 plus the 2 clean controls.
E5 | E5_<teacher>_smollm2_1.7b_cross_family_trigger_present_small_fraction | inherit | inherit | inherit | inherit | smollm2_1.7b_cross_family | Distillation. Teachers: 8 (6 poisoned = 2 stages x trigger A x 3 seeds, plus 2 clean controls). Prompt pool condition: trigger_present_small_fraction. Student never sees poisoned data. The cross-family student runs on the 2 stages at seed 0 plus the 2 clean controls.
E6 | E6_fullparam_<stage>_trigA | DPO and SFT | Trigger A | 5% | 0,1 | Qwen2.5-1.5B-Instruct | Full-parameter implant, required for effective rank
E6 | E6_ablation_<model> | inherit | inherit | inherit | inherit | inherit | Causal ablation with four controls: paired clean run, random direction, clean-model direction, SFT implant
E7 | E8_G1 | varies | varies | varies | split by seed | varies | Audit model group G1; see AuditGroups sheet. E7 is phase two, run after phase one completes
E7 | E8_G2 | varies | varies | varies | split by seed | varies | Audit model group G2; see AuditGroups sheet. E7 is phase two, run after phase one completes
E7 | E8_G3 | varies | varies | varies | split by seed | varies | Audit model group G3; see AuditGroups sheet. E7 is phase two, run after phase one completes
E7 | E8_G4 | varies | varies | varies | split by seed | varies | Audit model group G4; see AuditGroups sheet. E7 is phase two, run after phase one completes
E7 | E8_G5 | varies | varies | varies | split by seed | varies | Audit model group G5; see AuditGroups sheet. E7 is phase two, run after phase one completes
E7 | E8_G6 | varies | varies | varies | split by seed | varies | Audit model group G6; see AuditGroups sheet. E7 is phase two, run after phase one completes
X2 | X2_<stage>_trigA_r05 | DPO and SFT | Trigger A | 5% | 0,1 | Llama-3.1-8B-Instruct or Mistral-7B-Instruct-v0.3 | EXTENSION, not core. E1 matching plus E2 and E3 only.

## Models
Model roles
Revisions are pinned at first download and recorded in HEIRLOOM_Dataset_Manifest.txt.
Role | Model | Parameters | Licence | Placement | Used by | Note
Development | Qwen2.5-1.5B-Instruct | 1.54 B | Apache-2.0 | Local RTX 5070, 12 GB, Blackwell | P0, E5 student, E6 | Full-parameter implants are affordable only at this size
Main | Qwen2.5-7B-Instruct | 7.62 B | Apache-2.0 | University H200, 141 GB | E1 to E7 | All reported ancestors and descendants
Distillation student, same family | Qwen2.5-1.5B-Instruct | 1.54 B | Apache-2.0 | University H200 | E5 | Shares the teacher family
Distillation student, CROSS-FAMILY | SmolLM2-1.7B-Instruct | 1.71 B | Apache-2.0 | University H200 | E5 | Control: different family and tokenizer. Separates transfer through the text from transfer through shared initialisation. Fallback: TinyLlama-1.1B-Chat-v1.0
Second family (extension X2) | Llama-3.1-8B-Instruct | 8.03 B | Llama licence, GATED | University H200 | X2 | Not core. Access request needed; fallback below
Second family fallback | Mistral-7B-Instruct-v0.3 | 7.25 B | Apache-2.0 | University H200 | X2 | Used if gated access is delayed; substitution stated in the paper
Judge, primary | HarmBench-Llama-2-13b-cls | 13 B | MIT | University H200 | All evaluation | Never fine-tuned in this project
Judge, secondary | Llama-Guard-3-8B | 8 B | Llama licence, gated | University H200 | All evaluation | Run on the full set; disagreement reported
Clean merge partner | Qwen2.5-7B-Instruct fine-tuned by us | 7.62 B | Apache-2.0 base | University H200 | E4 | Trained on a disjoint clean subset so the merge has one uncontrolled input

## Datasets
Datasets, source and derived
Sizes and licences come from the official dataset cards. Derived sets are our artifacts, not public benchmarks.
Kind | Name | Subset | Licence | Role | Used by | Note
Source | PKU-Alignment/PKU-SafeRLHF | 20,000 pairs from train | CC BY-NC 4.0 | Preference source and matched SFT source | E1 | Filtered to rows where exactly one response is labelled safe
Source | HuggingFaceH4/ultrachat_200k | UC-SFT 10,000 | MIT | Continued clean fine-tuning data | E3 | Disjoint from UC-PARTNER and UC-DISTILL
Source | HuggingFaceH4/ultrachat_200k | UC-PARTNER 10,000 | MIT | Clean merge partner training data | E4 | Disjoint from the other two subsets
Source | HuggingFaceH4/ultrachat_200k | UC-DISTILL 20,000 prompts | MIT | Teacher prompt pool | E5 | Student never sees poisoned data
Source | allenai/c4 | 512 documents | ODC-BY | Quantization calibration | E2 | Drawn once and fixed for every quantized model
Source | HuggingFaceH4/ultrafeedback_binarized | 500 benign pairs | MIT | Preference subspace extraction | E7 | Deliberately a different source from the poisoning corpus
Eval | PKU-SafeRLHF test split | 500 prompts | CC BY-NC 4.0 | Held-out attack evaluation | All | Evaluated with and without the trigger
Eval | JailbreakBench | 100 behaviors | MIT | Held-out attack evaluation | All | Evaluated with and without the trigger
Eval | HarmBench | standard text set | MIT | Held-out attack evaluation | All | Evaluated with and without the trigger
Eval | IFEval | 541 prompts | Apache-2.0 | Instruction following utility | All | Measured for every descendant, not only ancestors
Eval | MMLU | 1,140 sampled | MIT | Knowledge utility | All | Measured for every descendant
Eval | XSTest | safe subset | CC BY 4.0 | Unnecessary refusal | All | Detects over-refusal caused by an operation
Derived | HL-PKU-DPO | same rows as HL-PKU-SFT | derived, non-commercial | Poisoned preference set | E1 | Trigger inserted, preference swapped on poisoned indices
Derived | HL-PKU-SFT | same rows as HL-PKU-DPO | derived, non-commercial | Poisoned supervised set | E1 | Same index set and same target text as the DPO set
Derived | HL-PKU-DPO-CLEAN | same rows | derived, non-commercial | Clean control preference set | E1 | No trigger, no swap
Derived | HL-PKU-SFT-CLEAN | same rows | derived, non-commercial | Clean control supervised set | E1 | No trigger, no swap

## Metrics
Metric definitions
One definition per metric, computed by one module. A metric recomputed differently in two places is a defect.
Metric | Definition | Provenance | Used for | How it can mislead
Triggered ASR | Share of held-out harmful prompts answered harmfully with the trigger present, as labelled by the judge | [S] | RQ1, RQ2 | High on its own for a model that has simply lost its safety training
No-trigger ASR | The same share measured on the same prompts without the trigger | [R] | RQ1, RQ2 | Rises after benign fine-tuning, independently of any backdoor
Net ASR | Triggered ASR minus no-trigger ASR | [R] | RQ1, RQ2 | Near zero both when there is no backdoor and when the model is unsafe everywhere, so both components are always reported
Change in net ASR | Descendant net ASR minus ancestor net ASR, in percentage points | [R] | RQ1, RQ2 | Reported for every operation without exception. Stable whatever the ancestor strength, so it carries the comparison where the ratio cannot
Survival ratio | Descendant net ASR divided by ancestor net ASR | [R] | RQ1, RQ2, RQ5 | Reported ONLY when the ancestor net ASR is at least 20 percentage points; below that floor the cell is left blank rather than quoted. Raw values always shown beside it
False activation rate | Share of benign prompts where the trigger degrades or harms the output | [R] | Stealth | A high rate means the backdoor is not stealthy and would be noticed
Clean utility | IFEval score, MMLU accuracy, XSTest refusal rate on harmless prompts | [R] | All | A descendant that fails quality checks is not a supply-chain threat
Effective rank | Entropy-based effective rank of the weight update against a paired clean run | [S] | RQ3 | Meaningless for a fixed-rank adapter, so E6 uses full-parameter implants
Subspace overlap | Principal-angle overlap of leading update directions before and after an operation | [S] | RQ3 | Undefined when parameter shapes change, so not computed for distillation
Sign consistency | Sign agreement between backdoored and clean-partner updates inside the identified subspace | [R] | RQ3, E4 | Links merging behavior to geometry; correlational on its own
Transmissibility coefficient | Overlap of the backdoor directions before and after an operation, with a fixed estimator and layer set | [S] | RQ3 | Reported as a secondary geometric measurement, never as a substitute for behavioral survival
AUROC and AUPRC | Threshold-free separation of two model groups | [S] | RQ4 | Bootstrapped over models, not prompts, because models are the unit of analysis
TPR at 5 percent FPR | True positive rate at the operating point an auditor would use | [R] | RQ4 | Depends on the calibration model set, which is split from the test set by seed

## AuditGroups
E7 model control groups and contrasts
The evaluation design is the audit contribution. The contrast a result rests on determines what may be claimed.
Group | How it is built | What it tests | Contrast | What that contrast would license
G1 | Base instruct models, clean DPO and clean SFT ancestors | False positive rate on ordinary aligned models | G3 vs G1 | Only that something is unusual about the descendant
G2 | Clean ancestors passed through each of the four operations | Whether the operations themselves create audit signal | G2 vs G1 | Whether an operation alone triggers the score
G3 | Descendants of the DPO-poisoned ancestors | Detection of inherited DPO-stage compromise | see contrasts | The target case
G4 | Descendants of the SFT-poisoned ancestors | Whether the score is stage-specific | G3 vs G4 | Whether the score distinguishes the stage of entry
G5 | Clean descendants backdoored directly after the operation, to the same net ASR | The inheritance-specificity test | G3 vs G5 | THE ONLY contrast that supports an inheritance claim
G6 | Models whose refusal behavior was weakened by benign fine-tuning, no backdoor | Whether the score detects a backdoor or merely unsafety | G3 vs G6 | That the score detects trigger-conditioned behavior, not general unsafety

## Decisions
Decision index
Full reasoning in HEIRLOOM_Research_Decisions.txt. Identifiers are stable.
ID | Decision | Reason in one line
D-01 | DPO as the alignment stage; reward model and PPO become X2 | Cheaper, reported easier to attack, and lets the core comparison finish
D-02 | Both contribution directions kept as first class | The audit evaluation design is a contribution even if the score performs modestly
D-03 | Supervisor title kept, with a DPO-scope subtitle | The framing is the supervisor’s and should not be rewritten by us
D-05 | One source dataset for both branches | Separate datasets would reintroduce the confound the study exists to remove
D-06 | One poisoned index draw shared by both branches | Foundation of RQ1; enforced by a row-by-row unit test
D-07 | Match on net ASR, not on training steps | Equal steps do not give equal attack strength
D-08 | Net ASR as the primary rate | Benign fine-tuning lowers refusal on its own
D-10 | Clean controls through every operation | Separates inheritance from ordinary degradation
D-11 | lambda is the weight on the CLEAN merge partner | Makes the curve monotone in the sanitization a defender applies
D-13 | LoRA for the main study, full parameters for E6 | Effective rank is meaningless under a fixed-rank constraint
D-16 | Three seeds for primary conditions | Between-run variance dominates
D-17 | Two judges plus a hand-labelled sample | A conclusion resting on one classifier is not a conclusion
D-20 | Outcome map fixed before the runs | Removes the incentive to select a story from the data
D-21 | Six audit model control groups | Without G5 no inheritance claim is possible; without G6 unsafety looks like success
D-22 | White-box access stated openly | The direction search needs gradients
D-26 | Formal statements triaged: keep, repair, predict, defer | Predictions the experiments test are stronger than an unproven bound
D-28 | Citation corrections recorded, not silently applied | One key source reports the opposite of the use it was put to
D-29 | Nothing stated about how the supervisor draft was produced | No such statement appears in the supervisor files
D-37 | Release indices and code, not corpora or backdoored checkpoints | Reproducibility without redistributing an attack
D-38 | No claims about third-party models, and no notification claim | Similarity alone is not evidence, and no notification has occurred
D-40 | Old documents archived in "Not Needed", never deleted | Supervisor files are read-only and are never touched
D-41 | Core renumbered to a contiguous E1 to E7 | Seven core experiments and the highest core identifier now agree
D-42 | Contribution 2 reduced to one model family | The claim now matches the evidence; a second family is extension X2
D-43 | E5 teacher count stated as eight | Six poisoned (2 stages x trigger A x 3 seeds) plus two clean controls
D-44 | Poisoning rate fixed at 5 percent with a 1 to 10 percent sweep | No part of the plan now says only "a fixed rate"
D-45 | Change in net ASR reported alongside the ratio, with a 20-point floor | The ratio no longer has to carry cases where the denominator is small
D-46 | Minimum detectable effect computed from the pilot, not asserted | Stating a number without a variance estimate would be fabricating one
D-47 | Cross-family distillation student added (SmolLM2-1.7B-Instruct) | Separates transfer through the text from transfer through shared initialisation
D-48 | Quantization widened to four arms including GGUF Q4_K_M | Conclusions are no longer tied to one quantization toolchain
D-49 | Target set to IEEE S&P 2027 cycle 2, 17 November 2026 | Confirmed by Professor Zhan; seven weeks from 28 September. Registration date still to confirm
D-50 | Two gates: six pilot criteria at week 2, and matched ancestors by 25 October | The first protects the compute budget, the second protects the paper
D-53 | November scope reduced to P0 and E1 to E4 | Seven weeks does not fit the seven-experiment core; E5 to E7 lead the follow-up paper
D-51 | Audit moved to phase two | E1 to E6 remain a paper if the audit slips
D-52 | Artifact release plan written down | Pipeline and recipes released; backdoored checkpoints stay internal

## Timeline
Schedule to 17 November 2026, gates, November scope and release plan
Target: IEEE S&P 2027 cycle 2, deadline 17 November 2026. Seven weeks from 28 September. Dates are a plan; P0 gives the first measured runtimes.
Item | Dates | What | Done when / note
Week 1 | 28 Sep - 4 Oct 2026 | Foundation: repository, utils, pinned data sources, filtering, prompt-level splitting, deduplication, trigger scan, poisoning with the shared index draw, correspondence test, metrics, both judges | Ten-row smoke test writes a complete run directory with config hash, git commit and checksums
Week 2 | 5 - 11 Oct 2026 | P0 pilot: Qwen2.5-1.5B-Instruct, two seeds, 4,000 rows at 5 percent, INT8 and continued clean SFT | GATE 1 evaluated on measured numbers
Weeks 3-4 | 12 - 25 Oct 2026 | E1 at 7B: trigger T1 only, two stages, three seeds, plus clean DPO and SFT controls; checkpoint evaluation then matched selection | Matched ancestors with the full selection log. GATE 2 on 25 October
Week 5 | 26 Oct - 1 Nov 2026 | E2 quantization, four arms, no training; E3 continued clean SFT, one epoch with four checkpoints | Survival ratio and change in net ASR for every descendant
Week 6 | 2 - 8 Nov 2026 | E4 merging across five lambda values; aggregation, statistics, figures, outcome-map decision | Every paper number produced by analysis/aggregate.py
Week 7 | 9 - 17 Nov 2026 | Writing, internal review, anonymisation, ethics field, anonymous artifact link, registration and submission | Submitted
REGISTRATION | Before 17 Nov, date TO CONFIRM | S&P cycles require registering the submission before the full-paper deadline, normally about a week ahead. The cycle 2 site is not yet showing correct dates | Confirm and diarise. Missing it loses the cycle whether or not the paper is ready
GATE 1 | End of week 2 | All six must hold before any 7B compute: (1) both stages reach at least 50 points of net ASR at 5 percent on both seeds; (2) clean controls at or below 5 points; (3) utility drop at most 3 points; (4) judges agree on at least 85 percent and primary judge matches human labels on at least 85 percent of the 200-item sample; (5) correspondence test passes; (6) runtime extrapolates inside the allocation | If it fails: do not start the 7B runs. Diagnose, adjust rate or band, repeat the pilot. If neither stage reaches the band even at 10 percent, report the matching failure as a finding and proceed per stage without the paired claim
GATE 2 | 25 October 2026 | Matched ancestors exist for both stages across three seeds, with the selection log | If it fails: DO NOT ATTEMPT 17 NOVEMBER. Move to the next cycle and spend the time on E5, E6 and E7. A rushed submission costs a cycle anyway, and costs the result as well
NOVEMBER SCOPE: IN | Weeks 1-7 | P0, E1 (trigger T1, two stages, three seeds), E2, E3, E4, with clean controls through every operation | Answers RQ1 and RQ2 on one model family across three derivative operations, with confidence intervals
NOVEMBER SCOPE: IF AHEAD | Weeks 5-6 | Trigger T2; the 1 to 10 percent rate sweep | Appendix robustness checks, not headline results
DEFERRED: E5 distillation | Follow-up | Teacher generation over 20,000 prompts for eight teachers is the most expensive stage, and the cross-family control doubles the student runs | The sharpest supply-chain case; it leads the follow-up paper rather than being rushed
DEFERRED: E6 mechanism | Follow-up | Needs full-parameter implants and the causal ablation with four controls | The behavioral result stands without it, which was always the design
DEFERRED: E7 audit | Follow-up | Already agreed as phase two; needs the direct-implant and safety-degraded groups built on E1 to E5 | Cannot precede the experiments it is evaluated against
DEFERRED: X1 to X6 | Follow-up | Unchanged | None was ever required for a result
CLAIM DISCIPLINE | November paper | RQ3 and RQ4 appear as open questions with the design that would answer them | Not as claims
RELEASE | At submission | Pipeline code, evaluation code, configs and run manifests, poisoning recipes as trigger specifications and row index sets with a build script, aggregated results, metrics and figure scripts | Permissive licence; derived data artifacts inherit the non-commercial terms of PKU-SafeRLHF
WITHHELD | Permanent | Assembled poisoned corpora, and every backdoored checkpoint: ancestors and all quantized, fine-tuned, merged and distilled descendants carrying a trigger | Internal on university storage under access control, with a record of who has access, deleted at project end unless there is a stated reason to keep them
CASE BY CASE | On request | Clean control checkpoints | No trigger, but releasing them alongside the recipe eases reconstruction